## Project Planner
Application Development Timeline
[5 empty] | Period Highlight: | -9 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | time axis 2017-09-13 to 2017-11-27
 | time axis 2017-09-13 to 2017-11-27
Gather Software Requirements | 1 | 1 | 1 | 1 | 0%
Intial Design Aspects | 1 | 5 | 1 | 5 | 0%
Initial Software Development Plan | 1 | 8 | 1 | 8 | 0%
Software Requirement Specification | 6 | 8 | 6 | 8 | 0%
Operatonal Server Side | 10 | 20 | 10 | 20 | 0%
Operatonal Client Side | 10 | 20 | 10 | 20 | 0%
Server Documentation | 10 | 51 | 10 | 51 | 0%
Client Application Documentation | 10 | 51 | 10 | 51 | 0%
First Northwood Meeting | 20 | 1 | 20 | 1 | 0%
Readjust Software Requirements | 21 | 2 | 21 | 2 | 0%
Integrate Client & Sever | 30 | 11 | 30 | 11 | 0%
Testing / Testing Report | 41 | 10 | 41 | 10 | 0%
Adjust Based on Testing | 51 | 10 | 51 | 10 | 0%
Refine Software Deleopment Plan | 51 | 10 | 51 | 10 | 0%
Second Northwood Meeting | 55 | 1 | 55 | 1 | 0%
Publish Documenation | 62 | 2 | 62 | 2 | 0%
Third Northwood Meeting | 69 | 1 | 69 | 1 | 0%
Deploy Application | 69 | 3 | 69 | 3 | 0%